## Instructions
P.R.I.S.M UAT Form - How to use
Steps
1 | Open the UAT Form sheet. Choose your role in "What is your user role?".
2 | Choose one module in "What module would you test?". Only modules for your role are listed.
3 | Enter your tester name and test date.
4 | Do each test case and pick its Satisfaction Level.
5 | For Partially Passed or Skipped, write a comment in the format: Test Case ID - Comment.
6 | When Submission status shows READY TO SUBMIT, copy the Submission rows (J13:R18) and paste them as values into the next empty rows of Responses.
7 | Clear the yellow cells and choose your next module. One submission per module.
Satisfaction Level
| Passed - Working | The test case works as expected.
| Partially Passed - Works but needs revision (w/ comment) | It works but needs revision. A comment is required.
| Fail - Not working | It does not work.
| Skipped - Di tinest (w/ comment) | Not tested. A comment is required.
Comment question
IF YOU SELECT PARTIALLY PASSED OR SKIPPED Please may we know your suggestion or the part that need to improve STRICTLY
Format: Test Case ID - Comment
Legend
| Yellow cells | Fill these in. Everything else is calculated.
| Grey cells | Calculated. Do not type here.
Example (Client, CL-INQ · Public Inquiry)
| CL-INQ-01 - Open the inquiry form | Passed - Working
| CL-INQ-02 - Required contact details | Partially Passed - Works but needs revision (w/ comment) | CL-INQ-02 - No message appears when a required field is blank
| CL-INQ-05 - Submit the inquiry | Skipped - Di tinest (w/ comment) | CL-INQ-05 - Did not test because the API was offline
Sheets
| UAT Form | Answer one module at a time.
| Test Cases | All 197 test cases across 5 roles and 51 modules. Filter by role or module.
| Responses | One row per test case result. Each module submission adds its rows here.
| Summary | Results per role and module, calculated from Responses.

## UAT Form
P.R.I.S.M UAT Form
Fill the yellow cells. One submission per module: after finishing, copy the Submission rows (columns J to R) into the Responses sheet, then clear the yellow cells and choose your next module.
What is your user role?
What module would you test?
Tester name
Test date
Before you start
Module check
Submission status
Submission rows: copy J13:R18, then Paste Special > Values into the next empty rows of Responses
# | Test Case ID | Test Case | Steps | Expected Result | Satisfaction Level | Comment Format: Test Case ID - Comment | Check | Submission ID | Test Date | Tester | User Role | Module | Test Case ID | Test Case | Satisfaction Level | Comment
1
2
3
4
5
6
Note on G12: IF YOU SELECT PARTIALLY PASSED OR SKIPPED Please may we know your suggestion or the part that need to improve STRICTLY Format: Test Case ID - Comment Example: CL-INQ-02 - No message appears when a required field is blank

## Test Cases
Role | Module ID | Module | Test Case ID | Test Case | Steps | Expected Result | Before You Start
Client | CL-INQ | CL-INQ · Public Inquiry | CL-INQ-01 | Open the inquiry form | On the home page click Start inquiry. | The inquiry form opens on step 1 (Contact Info) and the stepper shows 4 steps. | Stay signed out. Open the client portal home page.
Client | CL-INQ | CL-INQ · Public Inquiry | CL-INQ-02 | Required contact details | Leave Full Name blank and click Continue. Then fill Full Name, Email, Phone, Client Type and Referral Source and click Continue. | You cannot move on while a required field is blank. With all required fields filled you reach step 2 (Event Details). | Stay signed out. Open the client portal home page.
Client | CL-INQ | CL-INQ · Public Inquiry | CL-INQ-03 | Event details and date rules | Try to pick a preferred date before today. Then fill Event Name, Event Type, a future Preferred Date and Expected Guests, and click Continue. | Past dates cannot be picked. With valid details you reach step 3 (Budget & Notes). | Stay signed out. Open the client portal home page.
Client | CL-INQ | CL-INQ · Public Inquiry | CL-INQ-04 | Budget, priority and review | Choose a budget range and an inquiry priority, click Continue, then click Back on step 4 and return. | Step 4 shows a summary that matches what you entered. Back keeps your answers. | Stay signed out. Open the client portal home page.
Client | CL-INQ | CL-INQ · Public Inquiry | CL-INQ-05 | Submit the inquiry | On step 4 try to submit without ticking the accuracy box, then tick it and submit. | Submit stays disabled until the box is ticked. After submit a success screen with a reference number and Submit another inquiry appears. | Stay signed out. Open the client portal home page.
Client | CL-ACC | CL-ACC · Sign-in and Account Access | CL-ACC-01 | Sign in | Open Sign in, enter the client email and password, and use the eye icon to show the password before signing in. | The password can be shown and hidden. A Signed in message appears and the dashboard opens. | Use the client account issued for UAT.
Client | CL-ACC | CL-ACC · Sign-in and Account Access | CL-ACC-02 | Wrong password | Sign in with the right email and a wrong password. | An error message appears and you stay on the sign-in page. | Use the client account issued for UAT.
Client | CL-ACC | CL-ACC · Sign-in and Account Access | CL-ACC-03 | Wrong portal account | Sign in here with a supplier or PMCM account. | You are refused with a message that names the correct portal. | Use the client account issued for UAT.
Client | CL-ACC | CL-ACC · Sign-in and Account Access | CL-ACC-04 | Protected pages | While signed out, open the /dashboard address directly. Sign in on the page that appears. | You are sent to sign in first, then returned to the dashboard after signing in. | Use the client account issued for UAT.
Client | CL-ACC | CL-ACC · Sign-in and Account Access | CL-ACC-05 | Password reset request | Click Forgot password, enter your email and click Request reset. | A status message confirms the request. | Use the client account issued for UAT.
Client | CL-ACC | CL-ACC · Sign-in and Account Access | CL-ACC-06 | Sign out | Sign out, then press the browser Back button. | You are signed out and the dashboard is not shown again without signing in. | Use the client account issued for UAT.
Client | CL-CON | CL-CON · Conforme | CL-CON-01 | View the conforme | From the dashboard click Review conforme. | The conforme text, version and status are shown. If there are several versions you can switch between them. | Needs a client account with a conforme issued by PMCM.
Client | CL-CON | CL-CON · Conforme | CL-CON-02 | Consent before acknowledging | Try Acknowledge conforme without ticking the consent box, then tick it. | The button stays disabled until the box is ticked. | Needs a client account with a conforme issued by PMCM.
Client | CL-CON | CL-CON · Conforme | CL-CON-03 | Acknowledge the conforme | Tick the consent box and click Acknowledge conforme. | Status changes to Awaiting PMCM countersignature. | Needs a client account with a conforme issued by PMCM.
Client | CL-CON | CL-CON · Conforme | CL-CON-04 | Countersigned conforme | After PMCM countersigns, reopen the conforme. | Status shows Complete. | Needs a client account with a conforme issued by PMCM.
Client | CL-DSH | CL-DSH · Dashboard and My Events | CL-DSH-01 | Action center | Open the dashboard home. | Needs your action and Waiting on PMCM lists are shown, together with Recent updates from PMCM. | Sign in with a client account that has at least one event.
Client | CL-DSH | CL-DSH · Dashboard and My Events | CL-DSH-02 | Event tabs | Open My events and switch between All, Upcoming, In planning, Completed and Cancelled. | Each tab shows only the events in that state. | Sign in with a client account that has at least one event.
Client | CL-DSH | CL-DSH · Dashboard and My Events | CL-DSH-03 | Search events | Type part of an event name in the search box. | The list narrows to matching events. | Sign in with a client account that has at least one event.
Client | CL-DSH | CL-DSH · Dashboard and My Events | CL-DSH-04 | Open an event | Click an event card. | The event workspace opens on the Overview tab for that event. | Sign in with a client account that has at least one event.
Client | CL-REQ | CL-REQ · New Event Request | CL-REQ-01 | Required fields and consent | Click New request. Leave Event name blank, then fill Event name, Event date and Planning notes without ticking privacy consent. | The request cannot be submitted until the required fields are filled and consent is ticked. | Sign in as a client.
Client | CL-REQ | CL-REQ · New Event Request | CL-REQ-02 | Submit a request | Fill the required fields, tick consent and submit. | A New event request submitted message appears. | Sign in as a client.
Client | CL-EVT | CL-EVT · Event Workspace and Change Requests | CL-EVT-01 | Workspace tabs load | Open the Overview, Details, Schedule, Guests and Progress tabs. | Each tab loads your event data without errors. Guests shows the guest count and access code. | Open one of your events.
Client | CL-EVT | CL-EVT · Event Workspace and Change Requests | CL-EVT-02 | Action shortcuts | Open the Actions tab and click an action item. | The matching event tab opens. | Open one of your events.
Client | CL-EVT | CL-EVT · Event Workspace and Change Requests | CL-EVT-03 | Submit a change request | On Overview, submit a change request with a title, area and details. Try once with the details blank. | Blank details are refused. A complete request appears in the change request list. | Open one of your events.
Client | CL-EVT | CL-EVT · Event Workspace and Change Requests | CL-EVT-04 | Withdraw a change request | Withdraw the open change request you created. | The request shows as withdrawn. | Open one of your events.
Client | CL-EVT | CL-EVT · Event Workspace and Change Requests | CL-EVT-05 | Request an ocular visit | Open the Changes tab and click Request ocular visit, with an optional note. | The request is recorded and shown. | Open one of your events.
Client | CL-EVT | CL-EVT · Event Workspace and Change Requests | CL-EVT-06 | Acknowledge an addendum | If PMCM issued an addendum, tick the consent box and acknowledge it. | The addendum shows as acknowledged. | Open one of your events.
Client | CL-BRF | CL-BRF · Briefing and Proposal | CL-BRF-01 | Briefing validation | Open the Briefing tab and submit with guest count 0 or blank required fields. | The briefing is refused until venue, guest count (at least 1), budget range, service requirements and notes are filled. | Open an event in planning. Proposal cases need PMCM to issue a proposal first.
Client | CL-BRF | CL-BRF · Briefing and Proposal | CL-BRF-02 | Submit and resubmit the briefing | Fill the briefing and submit. Change one field and submit again. | Both submissions are saved and the latest values are shown. | Open an event in planning. Proposal cases need PMCM to issue a proposal first.
Client | CL-BRF | CL-BRF · Briefing and Proposal | CL-BRF-03 | Approve the proposal | Open the Proposal tab and click Approve. | The proposal shows as approved. | Open an event in planning. Proposal cases need PMCM to issue a proposal first.
Client | CL-BRF | CL-BRF · Briefing and Proposal | CL-BRF-04 | Request a proposal revision | Click Request revision once without a note, then with a note. | A note is required. The revision is recorded. After 3 revisions, Revision cap reached is shown. | Open an event in planning. Proposal cases need PMCM to issue a proposal first.
Client | CL-BRF | CL-BRF · Briefing and Proposal | CL-BRF-05 | Venue and styling options | Approve one venue or styling option, and request revision on another with a note. | Approval is recorded. Revision needs a note and is recorded. | Open an event in planning. Proposal cases need PMCM to issue a proposal first.
Client | CL-FLR | CL-FLR · Floor Plan | CL-FLR-01 | Submit a layout preference | Fill Preference title, Guest count, Seating style, Stage preference and notes, then click Save layout notes. | The preference is sent and the form locks with PMCM has your preference. | Open an event and go to the Floor plan tab.
Client | CL-FLR | CL-FLR · Floor Plan | CL-FLR-02 | Resubmit after PMCM reopens | After PMCM reopens your preference, read the note and click Resubmit layout notes. | PMCM's note is shown and the updated preference is sent. | Open an event and go to the Floor plan tab.
Client | CL-FLR | CL-FLR · Floor Plan | CL-FLR-03 | Official layout is read-only | Click View official floorplan and try to move or edit items. | The official layout opens but cannot be edited by the client. | Open an event and go to the Floor plan tab.
Client | CL-FLR | CL-FLR · Floor Plan | CL-FLR-04 | Review an official layout | When a layout is in review, add an annotation to an item, then Approve or Request revision with a comment. | Annotations are saved. Approval locks the layout. Revision needs a comment. | Open an event and go to the Floor plan tab.
Client | CL-FLR | CL-FLR · Floor Plan | CL-FLR-05 | Shared floorplans | Open Shared floorplans from the menu and open a submitted or approved version. | Shared layouts are listed per event and open in a read-only viewer. | Open an event and go to the Floor plan tab.
Client | CL-FIL | CL-FIL · Files and Documents | CL-FIL-01 | Folder filters | Click each folder button (Contracts, Quotations, Invoices & receipts, Event layouts, Uploaded, Shared). | The list and counts change for each folder. | Select an event, then open Files.
Client | CL-FIL | CL-FIL · Files and Documents | CL-FIL-02 | Upload a file | Click Upload file and choose a small PDF. | The file uploads and appears in the list. | Select an event, then open Files.
Client | CL-FIL | CL-FIL · Files and Documents | CL-FIL-03 | Download a file | Click the download icon on a file. | The file downloads and opens correctly. | Select an event, then open Files.
Client | CL-FIL | CL-FIL · Files and Documents | CL-FIL-04 | File requirements | Look at the File requirements checklist. | Required files are listed with their due status. | Select an event, then open Files.
Client | CL-BIL | CL-BIL · Billing | CL-BIL-01 | Statement and milestones | Open Billing. | The billing statement, payment milestones and remaining balance are shown and match PMCM's records. | Select an event with a billing statement.
Client | CL-BIL | CL-BIL · Billing | CL-BIL-02 | Billing is read-only | Look for any way to edit a payment or amount. | There are no controls to change payments. Disputes show status and amount only. | Select an event with a billing statement.
Client | CL-MSG | CL-MSG · Messages | CL-MSG-01 | Send a message | Open Messages. Check Send with an empty box, then type a message and send it. | Send is disabled while empty. The message appears in the conversation. | Select an event where PMCM has opened a message thread.
Client | CL-MSG | CL-MSG · Messages | CL-MSG-02 | Receive and load history | Ask PMCM to reply, then reopen Messages and click Load older messages. | PMCM's reply is visible and older messages load. | Select an event where PMCM has opened a message thread.
Client | CL-CAL | CL-CAL · Calendar and Approvals | CL-CAL-01 | Calendar | Open Calendar and switch between Event dates, Deadlines, Payment due dates and Approval deadlines. | Today is highlighted and the schedule list changes per tab. | Select an event.
Client | CL-CAL | CL-CAL · Calendar and Approvals | CL-CAL-02 | Approvals overview | Open Approvals. | Proposal, Contracts, Quotations, Layouts and Final Confirmation show their current status. | Select an event.
Client | CL-CLO | CL-CLO · Event Closeout | CL-CLO-01 | Acknowledge wrap-up and deliverables | Open the Summary tab and acknowledge the wrap-up and each deliverable. | Each item shows as acknowledged. | Needs an event that PMCM has marked as wrapped up.
Client | CL-CLO | CL-CLO · Event Closeout | CL-CLO-02 | Rating and feedback | Give a rating and feedback. | Your rating and feedback are saved. | Needs an event that PMCM has marked as wrapped up.
Client | CL-CLO | CL-CLO · Event Closeout | CL-CLO-03 | Testimonial consent | Add a testimonial with consent, then withdraw the consent. | The testimonial is saved, then shows consent withdrawn. | Needs an event that PMCM has marked as wrapped up.
Client | CL-CLO | CL-CLO · Event Closeout | CL-CLO-04 | Archived event is read-only | Open an archived event. | It opens on Summary and nothing can be changed. | Needs an event that PMCM has marked as wrapped up.
Supplier | SU-APP | SU-APP · Supplier Application | SU-APP-01 | Company information | Leave Company Name blank and click Continue, then fill Company Name, Contact Person and Email. | You cannot continue with a blank required field. With them filled you reach Services & Portfolio. | Stay signed out. Open the supplier portal and go to Apply.
Supplier | SU-APP | SU-APP · Supplier Application | SU-APP-02 | Services and portfolio | Open the Service Category list and pick a category, then continue. | Categories load from the system and you reach Certifications. | Stay signed out. Open the supplier portal and go to Apply.
Supplier | SU-APP | SU-APP · Supplier Application | SU-APP-03 | Portfolio link check | Type an invalid Portfolio URL such as abc, then a valid https link. | The invalid link is refused and the valid link is accepted. | Stay signed out. Open the supplier portal and go to Apply.
Supplier | SU-APP | SU-APP · Supplier Application | SU-APP-04 | Submit the application | On Review & Submit, try Submit without the privacy consent, then tick it and submit. | Submit needs consent. Application submitted is shown with a reference number. | Stay signed out. Open the supplier portal and go to Apply.
Supplier | SU-APP | SU-APP · Supplier Application | SU-APP-05 | Check application status | Open Status and enter the reference and email. Then try a wrong email. | The correct pair shows the application status. A wrong pair shows a could not find error. | Stay signed out. Open the supplier portal and go to Apply.
Supplier | SU-ACC | SU-ACC · Sign-in and Account Access | SU-ACC-01 | Sign in | Sign in with the supplier email and password. | The supplier dashboard opens. | Use the approved supplier account issued for UAT.
Supplier | SU-ACC | SU-ACC · Sign-in and Account Access | SU-ACC-02 | Wrong password | Sign in with a wrong password. | A red error appears and you stay on sign-in. | Use the approved supplier account issued for UAT.
Supplier | SU-ACC | SU-ACC · Sign-in and Account Access | SU-ACC-03 | Wrong portal account | Sign in with a client or PMCM account. | You are refused with a wrong-portal message. | Use the approved supplier account issued for UAT.
Supplier | SU-ACC | SU-ACC · Sign-in and Account Access | SU-ACC-04 | Request PMCM approval | Expand Need supplier access?, try sending without consent, then tick consent and click Request PMCM approval. | Consent is required. A confirmation notice appears. | Use the approved supplier account issued for UAT.
Supplier | SU-ACC | SU-ACC · Sign-in and Account Access | SU-ACC-05 | Password reset request | Expand Need supplier access?, click Forgot password?, enter your email and click Request reset. | A status message confirms the request. | Use the approved supplier account issued for UAT.
Supplier | SU-ACC | SU-ACC · Sign-in and Account Access | SU-ACC-06 | Sign out | Click Sign out. | You return to sign-in and the dashboard needs a new sign-in. | Use the approved supplier account issued for UAT.
Supplier | SU-DSH | SU-DSH · Dashboard Overview and Calendar | SU-DSH-01 | Overview | Open Dashboard. | Greeting, stats and the readiness board grouped by event are shown. | Sign in as a supplier with at least one quote request or booking.
Supplier | SU-DSH | SU-DSH · Dashboard Overview and Calendar | SU-DSH-02 | Sidebar counts and refresh | Compare the sidebar badges with the Requests and Bookings pages, then click Refresh. | Badge counts match the pages and data reloads. | Sign in as a supplier with at least one quote request or booking.
Supplier | SU-DSH | SU-DSH · Dashboard Overview and Calendar | SU-DSH-03 | Calendar | Open Calendar. | Quote deadlines and event dates are listed. Past dates are struck through and today is labelled Today. | Sign in as a supplier with at least one quote request or booking.
Supplier | SU-QUO | SU-QUO · Quote Requests and Quotations | SU-QUO-01 | Submit a quote | Open Requests. Enter amount 0 and submit, then enter a valid amount, payment terms and inclusions and click Submit quote. | Amount 0 is refused. The valid quote is saved and the card shows the amount and status. | Needs an open quote request from PMCM.
Supplier | SU-QUO | SU-QUO · Quote Requests and Quotations | SU-QUO-02 | Revise a quote | Change the amount and click Save revision. | The revision number goes up and the new amount is shown. | Needs an open quote request from PMCM.
Supplier | SU-QUO | SU-QUO · Quote Requests and Quotations | SU-QUO-03 | Closed or selected request | Open a request that is closed, locked or already selected. | The form is read-only and the reason is shown. | Needs an open quote request from PMCM.
Supplier | SU-QUO | SU-QUO · Quote Requests and Quotations | SU-QUO-04 | Quotation history | Open Quotations. | Your quotes are listed with amount, revision, dates, payment terms and inclusions. | Needs an open quote request from PMCM.
Supplier | SU-QUO | SU-QUO · Quote Requests and Quotations | SU-QUO-05 | No access to other bids | Look through Requests and Quotations for other suppliers' quotes. | Only your own quotes are visible. | Needs an open quote request from PMCM.
Supplier | SU-BKG | SU-BKG · Bookings, Contracts and Event Day | SU-BKG-01 | Confirm assignment | Open Bookings and click Confirm assignment. | The button changes to Assignment confirmed. | Needs a booking where PMCM selected your quote.
Supplier | SU-BKG | SU-BKG · Bookings, Contracts and Event Day | SU-BKG-02 | Confirm readiness | Enter readiness notes and click Confirm readiness. | Readiness shows as confirmed on the progress tracker. | Needs a booking where PMCM selected your quote.
Supplier | SU-BKG | SU-BKG · Bookings, Contracts and Event Day | SU-BKG-03 | Upload signed contract | Try uploading a JPG, then upload a PDF or DOCX contract. | Only PDF or DOCX is accepted. The upload is listed with version, file name and review status, and can be downloaded. | Needs a booking where PMCM selected your quote.
Supplier | SU-BKG | SU-BKG · Bookings, Contracts and Event Day | SU-BKG-04 | Schedule acknowledgment | When PMCM publishes a schedule, click Acknowledge. On another, try Request change without a reason, then with a reason. | Acknowledgment is recorded. A change request needs a reason. | Needs a booking where PMCM selected your quote.
Supplier | SU-BKG | SU-BKG · Bookings, Contracts and Event Day | SU-BKG-05 | Creative tasks | On a creative task, save a progress note, then submit a deliverable with a note or file. | Progress and the deliverable are saved. PMCM's review note appears when given. | Needs a booking where PMCM selected your quote.
Supplier | SU-BKG | SU-BKG · Bookings, Contracts and Event Day | SU-BKG-06 | Event-day status | Before confirming assignment and readiness, check the event-day buttons. After both, set Arrived, then Set up and ready, then Done and leaving. | Buttons are disabled until both are confirmed. Each status is recorded. A Late arrival warning appears after the planned ingress time. | Needs a booking where PMCM selected your quote.
Supplier | SU-FIL | SU-FIL · Files, Payments and Profile | SU-FIL-01 | Files | Open Files and download a contract file. | The requirements matrix, contract files with review status and certifications are shown. Download works. | Sign in as a supplier with a booking.
Supplier | SU-FIL | SU-FIL · Files, Payments and Profile | SU-FIL-02 | Payments | Open Payments. | Milestones show scheduled, released and remaining amounts, due dates and release history. Nothing is editable. | Sign in as a supplier with a booking.
Supplier | SU-FIL | SU-FIL · Files, Payments and Profile | SU-FIL-03 | Profile | Open Services / Profile. | Your supplier details are shown read-only with a privacy notice. | Sign in as a supplier with a booking.
Supplier | SU-MSG | SU-MSG · Messages | SU-MSG-01 | Send a message | Open Messages, check Send with an empty box, then send a message. | Send is disabled while empty. The message appears in the thread. | Needs a booking linked to an event with a PMCM thread.
Supplier | SU-MSG | SU-MSG · Messages | SU-MSG-02 | Read replies and history | Open a thread with a PMCM reply and click Load older messages. | The reply is visible, the thread is marked read and older messages load. | Needs a booking linked to an event with a PMCM thread.
Guest | GU-OPN | GU-OPN · Open Event with Access Code | GU-OPN-01 | Preview the event | Open the guest portal, click Open with code, type the code in lowercase and click Preview event. | The code turns uppercase and the event name, client and date are shown. | Get the event access code from PMCM.
Guest | GU-OPN | GU-OPN · Open Event with Access Code | GU-OPN-02 | Wrong code | Enter a code that does not exist. | An error message is shown and no event opens. | Get the event access code from PMCM.
Guest | GU-OPN | GU-OPN · Open Event with Access Code | GU-OPN-03 | Continue to the dashboard | After preview, click Continue. | The guest dashboard for that event opens. | Get the event access code from PMCM.
Guest | GU-OPN | GU-OPN · Open Event with Access Code | GU-OPN-04 | Dashboard needs a code | In a private window, open the /dashboard address directly. | You are sent to the access-code page. | Get the event access code from PMCM.
Guest | GU-OPN | GU-OPN · Open Event with Access Code | GU-OPN-05 | Leave event | On the dashboard click Leave event. | The pass is cleared and the access-code page opens. | Get the event access code from PMCM.
Guest | GU-PAS | GU-PAS · Event Pass and Details | GU-PAS-01 | Event pass | Look at the event pass. | Event name, date and access code are shown. | Open an event with a valid code.
Guest | GU-PAS | GU-PAS · Event Pass and Details | GU-PAS-02 | Event details and next steps | Look at Event details and Your next steps. | Event, date, client, readiness and stage are shown. Next steps list check-in and feedback. | Open an event with a valid code.
Guest | GU-CHK | GU-CHK · Check-in | GU-CHK-01 | Consent required | Choose check-in by name, enter your registered name and try Submit check-in without consent. | Check-in cannot be submitted without consent. | Open an event that is not archived.
Guest | GU-CHK | GU-CHK · Check-in | GU-CHK-02 | Check in by name | Tick consent and submit. | The button changes to Check-in submitted and check-in shows as done in next steps. | Open an event that is not archived.
Guest | GU-CHK | GU-CHK · Check-in | GU-CHK-03 | Check in by headcount | With another code session, choose headcount, tick consent and submit. | The headcount check-in is accepted and locked. | Open an event that is not archived.
Guest | GU-FBK | GU-FBK · Feedback | GU-FBK-01 | Required fields and consent | Try to submit feedback without a name or without consent. | Feedback is refused until name and consent are given. | Open an event that has ended (feedback is open for 7 days after the event).
Guest | GU-FBK | GU-FBK · Feedback | GU-FBK-02 | File limits | Attach a photo over 10 MB, or a video longer than 60 seconds. | The file is rejected with an error message. | Open an event that has ended (feedback is open for 7 days after the event).
Guest | GU-FBK | GU-FBK · Feedback | GU-FBK-03 | Submit feedback | Enter name, choose 1 to 5 stars, add a comment, tick consent and submit. | Feedback is accepted and shown as complete in next steps. | Open an event that has ended (feedback is open for 7 days after the event).
Guest | GU-GAM | GU-GAM · Event Games | GU-GAM-01 | Join with PIN | Open Join game and enter 123 and then a wrong 6-digit PIN, then the real PIN. | Short PINs ask for 6 digits, wrong PINs show This game is unavailable, the real PIN joins with an alias such as Guest 1234. | Needs a game published by PMCM and its 6-digit PIN or lobby link.
Guest | GU-GAM | GU-GAM · Event Games | GU-GAM-02 | Event lobby | Open the lobby link from PMCM. | The event branding and the list of games are shown, each with a Start button. | Needs a game published by PMCM and its 6-digit PIN or lobby link.
Guest | GU-GAM | GU-GAM · Event Games | GU-GAM-03 | Play a round | Answer the current prompt and submit. | Your answer locks for the round and your score and standings update. | Needs a game published by PMCM and its 6-digit PIN or lobby link.
Guest | GU-GAM | GU-GAM · Event Games | GU-GAM-04 | Resume a session | Close the tab, reopen Join game and use the resume link. | You return to the same game session with the same alias. | Needs a game published by PMCM and its 6-digit PIN or lobby link.
PMCM Admin | AD-ACC | AD-ACC · Sign-in and Account Access | AD-ACC-01 | Sign in | Sign in with the admin email and password. | The PMCM dashboard opens with the full sidebar. | Use the PMCM admin account issued for UAT.
PMCM Admin | AD-ACC | AD-ACC · Sign-in and Account Access | AD-ACC-02 | Wrong password | Sign in with a wrong password. | An error appears and you stay on sign-in. | Use the PMCM admin account issued for UAT.
PMCM Admin | AD-ACC | AD-ACC · Sign-in and Account Access | AD-ACC-03 | Wrong portal account | Sign in with a client or supplier account. | You are refused with a link to the correct portal. | Use the PMCM admin account issued for UAT.
PMCM Admin | AD-ACC | AD-ACC · Sign-in and Account Access | AD-ACC-04 | Protected pages | While signed out, open /dashboard directly, then sign in. | You are sent to sign in, then back to the dashboard. | Use the PMCM admin account issued for UAT.
PMCM Admin | AD-ACC | AD-ACC · Sign-in and Account Access | AD-ACC-05 | Password reset request | Request a password reset by email. | A status message confirms the request. | Use the PMCM admin account issued for UAT.
PMCM Admin | AD-INB | AD-INB · Dashboard and Command Inbox | AD-INB-01 | Command inbox | Open the dashboard, refresh the inbox and change pages. | Inbox items load, the sidebar badge matches the count and paging works. | Sign in as admin.
PMCM Admin | AD-INB | AD-INB · Dashboard and Command Inbox | AD-INB-02 | Selected event summary | Select an event and click Open event on the summary card. | The summary matches the event and opens its workspace. | Sign in as admin.
PMCM Admin | AD-INB | AD-INB · Dashboard and Command Inbox | AD-INB-03 | Account requests | Approve one pending account request and decline another. | Each request leaves the pending list with the chosen result. | Sign in as admin.
PMCM Admin | AD-INQ | AD-INQ · Inquiries and Client Onboarding | AD-INQ-01 | Review a new inquiry | Open Inquiries and open the test inquiry. | The details match what the client submitted, with duplicate and previously-declined cues where they apply. | Submit a test inquiry from the client portal first.
PMCM Admin | AD-INQ | AD-INQ · Inquiries and Client Onboarding | AD-INQ-02 | Pend and decline | Pend one inquiry. Decline another, first without a reason, then with a reason. | Pend is recorded. Decline needs a reason. | Submit a test inquiry from the client portal first.
PMCM Admin | AD-INQ | AD-INQ · Inquiries and Client Onboarding | AD-INQ-03 | Merge duplicates | Merge a duplicate inquiry into its organization with a reason. | The merge needs a reason and shows in merge history. | Submit a test inquiry from the client portal first.
PMCM Admin | AD-INQ | AD-INQ · Inquiries and Client Onboarding | AD-INQ-04 | Log on behalf of a client | Log an inquiry on behalf of a client, including How did you hear about us. | The inquiry is created and marked as logged by PMCM. | Submit a test inquiry from the client portal first.
PMCM Admin | AD-INQ | AD-INQ · Inquiries and Client Onboarding | AD-INQ-05 | Accept and upload conforme | Accept the inquiry. Upload a non-PDF as the signed conforme, then a PDF under 10 MB. | Non-PDF files are refused. After the PDF upload the event workspace is created and the client can open their portal. | Submit a test inquiry from the client portal first.
PMCM Admin | AD-INQ | AD-INQ · Inquiries and Client Onboarding | AD-INQ-06 | Conforme reminder and follow-up | Send a conforme reminder, then generate a follow-up draft and click Approve and queue for delivery. | The reminder is recorded and the draft is queued, not sent instantly. | Submit a test inquiry from the client portal first.
PMCM Admin | AD-CLI | AD-CLI · Clients | AD-CLI-01 | Client list and details | Open Clients and open a client. | Contact, company, event and inquiry counts and balance are shown. | Sign in as admin.
PMCM Admin | AD-CLI | AD-CLI · Clients | AD-CLI-02 | Client events | Open the client's events view and click an event. | The event workspace opens. | Sign in as admin.
PMCM Admin | AD-CLI | AD-CLI · Clients | AD-CLI-03 | Archived event search | Search archived events by venue, event type or month. | Matching archived events are listed. | Sign in as admin.
PMCM Admin | AD-TSK | AD-TSK · Tasks and Ocular Visits | AD-TSK-01 | Schedule and complete an ocular | Open Tasks, schedule an ocular visit, then mark it complete. | Status changes to scheduled, then completed. | Needs an event with an ocular visit request.
PMCM Admin | AD-TSK | AD-TSK · Tasks and Ocular Visits | AD-TSK-02 | Waive an ocular | Waive an ocular visit without a reason, then with a reason. | A reason is required and the waiver is recorded. | Needs an event with an ocular visit request.
PMCM Admin | AD-TSK | AD-TSK · Tasks and Ocular Visits | AD-TSK-03 | Action center links | Click each action-center count. | Each link opens the matching list (inquiries, approvals, quotes, payments, checks). | Needs an event with an ocular visit request.
PMCM Admin | AD-OVR | AD-OVR · Event Overview, Briefing and Change Control | AD-OVR-01 | Briefing and compliance | On Overview submit the event briefing and run planning compliance. Open the Briefing tab. | The briefing is saved and shown on the Briefing tab. Compliance results appear. | Open an event in planning.
PMCM Admin | AD-OVR | AD-OVR · Event Overview, Briefing and Change Control | AD-OVR-02 | Scope change requests | Start review on a client change request, then approve or reject it with a reason. | The decision needs a reason and the client sees the new status. | Open an event in planning.
PMCM Admin | AD-OVR | AD-OVR · Event Overview, Briefing and Change Control | AD-OVR-03 | Freeze scope and exceptions | Freeze scope with a reason, then create and approve a freeze exception. | Freeze needs a reason. The exception is listed and used once. | Open an event in planning.
PMCM Admin | AD-OVR | AD-OVR · Event Overview, Briefing and Change Control | AD-OVR-04 | Cancellation or postponement | Record a postponement with a new date and deposit treatment (use a test event). | The impact review is shown and the decision is recorded. | Open an event in planning.
PMCM Admin | AD-OVR | AD-OVR · Event Overview, Briefing and Change Control | AD-OVR-05 | Secondary contacts and access code | Grant floorplan access to an approved client account. Check the guest access code. | The contact is added. The guest access code is shown, or Pending if not yet generated. | Open an event in planning.
PMCM Admin | AD-FLR | AD-FLR · Floorplans | AD-FLR-01 | Create from template | Start a new draft from a saved venue template. | The draft opens with the template layout. | Open an event and go to Floorplans.
PMCM Admin | AD-FLR | AD-FLR · Floorplans | AD-FLR-02 | Edit and save | Add and move items in the editor and save. | Changes are kept after reopening the draft. | Open an event and go to Floorplans.
PMCM Admin | AD-FLR | AD-FLR · Floorplans | AD-FLR-03 | Table assignment rules | Assign more guests to a table than it holds and save. | The save is refused with a clear reason. | Open an event and go to Floorplans.
PMCM Admin | AD-FLR | AD-FLR · Floorplans | AD-FLR-04 | Submit and approve | Submit a draft for review, then approve it. | Submit only shows for new or needs-revision drafts. Approve only shows for drafts in review. | Open an event and go to Floorplans.
PMCM Admin | AD-FLR | AD-FLR · Floorplans | AD-FLR-05 | Client preference | Open a client's submitted preference and reopen it with a note. | The client's preference is shown and the client can revise it again. | Open an event and go to Floorplans.
PMCM Admin | AD-SUP | AD-SUP · Event Suppliers | AD-SUP-01 | Request and compare quotes | Request quotes for a category, then compare received quotes and select one. | Suppliers receive the request. The selected quote is marked and others are closed. | Open an event and go to Suppliers.
PMCM Admin | AD-SUP | AD-SUP · Event Suppliers | AD-SUP-02 | Readiness board | Open the readiness board. | Each supplier's readiness is shown. A category with no selected quote shows a hard block. | Open an event and go to Suppliers.
PMCM Admin | AD-SUP | AD-SUP · Event Suppliers | AD-SUP-03 | Ingress schedule | Publish an ingress and egress schedule. | The supplier sees the schedule and can acknowledge it. | Open an event and go to Suppliers.
PMCM Admin | AD-SUP | AD-SUP · Event Suppliers | AD-SUP-04 | Contracts | Review a supplier contract upload and request a revision with a reason. | The supplier sees the revision request and reason. | Open an event and go to Suppliers.
PMCM Admin | AD-SUP | AD-SUP · Event Suppliers | AD-SUP-05 | Payables | Release a payable milestone, then reverse it. | Release and reversal are recorded and amounts update. | Open an event and go to Suppliers.
PMCM Admin | AD-SUP | AD-SUP · Event Suppliers | AD-SUP-06 | Emergency replacement | Withdraw a confirmed supplier (test event only). | A recommended replacement and draft messages are shown for PMCM to review. | Open an event and go to Suppliers.
PMCM Admin | AD-DIR | AD-DIR · Supplier Directory and Applications | AD-DIR-01 | Applications inbox | Open the test application and request a proposal, schedule a meeting or decline. | The status changes and the applicant sees it on the Status page. | Submit a test supplier application first.
PMCM Admin | AD-DIR | AD-DIR · Supplier Directory and Applications | AD-DIR-02 | Approve an application | Approve an application. | A directory supplier is created, pending its first event. | Submit a test supplier application first.
PMCM Admin | AD-DIR | AD-DIR · Supplier Directory and Applications | AD-DIR-03 | Create and edit a supplier | Create a supplier, then edit its profile, tier and BNI membership. | Changes are saved and shown in the directory. | Submit a test supplier application first.
PMCM Admin | AD-DIR | AD-DIR · Supplier Directory and Applications | AD-DIR-04 | Filters | Filter by category, tier and rating. | The list shows only matching suppliers. | Submit a test supplier application first.
PMCM Admin | AD-COR | AD-COR · Coordinators and Team | AD-COR-01 | Assign with suggestions | Pick a role and assign a coordinator from the suggestions. | Suggestions show skill match and the coordinator is assigned. | Open an event and go to Coordinators.
PMCM Admin | AD-COR | AD-COR · Coordinators and Team | AD-COR-02 | Same-date conflict | Assign a coordinator already booked on the same date. | The assignment is blocked and same-role alternatives are suggested. | Open an event and go to Coordinators.
PMCM Admin | AD-COR | AD-COR · Coordinators and Team | AD-COR-03 | Event Day System Operator | Designate a coordinator as Event Day System Operator. | The designation is shown and that coordinator gets operator controls. | Open an event and go to Coordinators.
PMCM Admin | AD-COR | AD-COR · Coordinators and Team | AD-COR-04 | Availability and reminders | Add an unavailable date for a coordinator and send an acknowledgment reminder. | The date blocks assignment and the reminder is recorded. | Open an event and go to Coordinators.
PMCM Admin | AD-COR | AD-COR · Coordinators and Team | AD-COR-05 | Reliability history | Open a coordinator's reliability history. | Past assignments and withdrawals are listed. | Open an event and go to Coordinators.
PMCM Admin | AD-LIV | AD-LIV · Live Ops and Run Sheet | AD-LIV-01 | Event-day tasks | Create a task with title, owner role, priority and SLA, then update and escalate it. | The task is listed and its status changes are shown. | Open an event near or on event day.
PMCM Admin | AD-LIV | AD-LIV · Live Ops and Run Sheet | AD-LIV-02 | Urgent issues | Log an issue with severity and area, then update it. | The issue is listed and its changes are shown. | Open an event near or on event day.
PMCM Admin | AD-LIV | AD-LIV · Live Ops and Run Sheet | AD-LIV-03 | Coordinator attendance | Mark coordinators present, late and absent. Replace an absent one using suggestions. | Attendance is recorded and the replacement is assigned. | Open an event near or on event day.
PMCM Admin | AD-LIV | AD-LIV · Live Ops and Run Sheet | AD-LIV-04 | Schedule and handoffs | Add a day and segments, record a shift handoff and reply to an end-of-day report. | Each entry is saved and shown. | Open an event near or on event day.
PMCM Admin | AD-LIV | AD-LIV · Live Ops and Run Sheet | AD-LIV-05 | Run sheet | Open Run sheet and print it. | Items are in time order and the print view is readable. | Open an event near or on event day.
PMCM Admin | AD-REG | AD-REG · Registration and Guests | AD-REG-01 | Registration setup | Set the registration platform type and min, max and expected guests. | The settings are saved. | Open an event and go to Registration.
PMCM Admin | AD-REG | AD-REG · Registration and Guests | AD-REG-02 | Guest roster | Import a guest roster, then search and filter it. | Guests are imported and search finds them. | Open an event and go to Registration.
PMCM Admin | AD-REG | AD-REG · Registration and Guests | AD-REG-03 | Check-in and verification | Verify and check in a guest from the roster. | The guest shows as verified and checked in. | Open an event and go to Registration.
PMCM Admin | AD-REG | AD-REG · Registration and Guests | AD-REG-04 | Walk-in and privacy settings | Set the walk-in policy open or closed with a threshold, and set guest privacy classification. | The settings are saved and apply at the registration desk. | Open an event and go to Registration.
PMCM Admin | AD-GAM | AD-GAM · Event Games | AD-GAM-01 | Create and configure | Create a game from the catalog and set its questions or options. | The draft is saved with your configuration. | Open an event and go to Games.
PMCM Admin | AD-GAM | AD-GAM · Event Games | AD-GAM-02 | Lobby and branding | Set the lobby logo and theme, copy the lobby URL and show the PIN. | Guests opening the URL see your branding. The PIN is shown when you choose. | Open an event and go to Games.
PMCM Admin | AD-GAM | AD-GAM · Event Games | AD-GAM-03 | Run the game | Publish, start, go to the next round and end the game while a guest plays. | The guest screen follows each step and the leaderboard updates. | Open an event and go to Games.
PMCM Admin | AD-GAM | AD-GAM · Event Games | AD-GAM-04 | Moderation and awards | Hide a guest answer and assign an award. | The hidden answer disappears from shared results and the award is recorded. | Open an event and go to Games.
PMCM Admin | AD-BIL | AD-BIL · Billing and Finance | AD-BIL-01 | Record a payment | Record a payment of 0, then more than the milestone balance, then a valid amount (Bank Transfer, Cheque or GCash). | 0 and over-balance amounts are refused. The valid payment updates the balance. | Open an event with a billing statement. Correction approval needs a second admin account.
PMCM Admin | AD-BIL | AD-BIL · Billing and Finance | AD-BIL-02 | Send the statement | Send the billing statement. | The send is logged in notification activity and the client sees the statement. | Open an event with a billing statement. Correction approval needs a second admin account.
PMCM Admin | AD-BIL | AD-BIL · Billing and Finance | AD-BIL-03 | Disputes and waivers | Record a dispute above the statement total, then a valid one, and resolve or waive it with a reason. | The over-total dispute is refused. Resolve or waive needs a reason. | Open an event with a billing statement. Correction approval needs a second admin account.
PMCM Admin | AD-BIL | AD-BIL · Billing and Finance | AD-BIL-04 | Additional billing | Issue additional billing from an approved billing source. | The additional billing appears on the statement. | Open an event with a billing statement. Correction approval needs a second admin account.
PMCM Admin | AD-BIL | AD-BIL · Billing and Finance | AD-BIL-05 | Correction needs a second admin | Request a correction, try to approve it with the same admin, then approve it with a second admin. | Approve is disabled for the requester. The second admin can approve. | Open an event with a billing statement. Correction approval needs a second admin account.
PMCM Admin | AD-CLO | AD-CLO · Closure and Archive | AD-CLO-01 | Record end and logistics | Record the actual end time. Try logistics completion before confirming asset returns, then after. | Logistics completion needs asset returns confirmed first and is then recorded. | Open an event that has ended (use a test event).
PMCM Admin | AD-CLO | AD-CLO · Closure and Archive | AD-CLO-02 | Wrap-up and close gates | Complete the wrap-up and review the close gates. | Must-fix and advisory gates are shown with their status. | Open an event that has ended (use a test event).
PMCM Admin | AD-CLO | AD-CLO · Closure and Archive | AD-CLO-03 | Archive rules | Try to archive with a failing gate and no reason, then give an override reason. | Archive is blocked without a reason and allowed with one. | Open an event that has ended (use a test event).
PMCM Admin | AD-CLO | AD-CLO · Closure and Archive | AD-CLO-04 | Reviews, testimonials and feedback | Add a supplier review, approve a client testimonial and approve or hide a guest feedback item. | Each decision is saved. Hidden feedback is not shown publicly. | Open an event that has ended (use a test event).
PMCM Admin | AD-CLO | AD-CLO · Closure and Archive | AD-CLO-05 | Compare archived events | Select 2 to 4 archived events and compare them. | A side-by-side comparison is shown. Fewer than 2 or more than 4 cannot be compared. | Open an event that has ended (use a test event).
PMCM Admin | AD-MSG | AD-MSG · Messages | AD-MSG-01 | Create a thread | On the event's Activity tab create a message thread and send a message. | The thread is created and the client can see the message. | Open an event with a client.
PMCM Admin | AD-MSG | AD-MSG · Messages | AD-MSG-02 | Reply and history | Reply to a client message and click Load older messages. | The reply is shown and older messages load. | Open an event with a client.
PMCM Admin | AD-FIL | AD-FIL · Files and Requirements | AD-FIL-01 | Requirements matrix | Add a requirement and set owner role, visibility, required flag and due date. | The requirement is saved and only the chosen roles can see it. | Select an event and open Files.
PMCM Admin | AD-FIL | AD-FIL · Files and Requirements | AD-FIL-02 | Document hub | Open the document hub and its links to floorplans, briefing, suppliers, billing and closure. | Each link opens the right area. | Select an event and open Files.
PMCM Admin | AD-AUD | AD-AUD · Audit Trail and Decision Log | AD-AUD-01 | Audit trail filters | Open Audit and filter by event, severity and user. | Your recent actions appear and filters narrow the list. | Sign in as admin after doing a few actions.
PMCM Admin | AD-AUD | AD-AUD · Audit Trail and Decision Log | AD-AUD-02 | Decision log | Open an event's Decision log tab. | Overrides, approvals and scope decisions are listed with their reasons. | Sign in as admin after doing a few actions.
PMCM Admin | AD-PRV | AD-PRV · Privacy Console | AD-PRV-01 | Queue and filters | Open Privacy and filter by type, status and owner. Assign a request to yourself. | The queue filters correctly and shows due dates. You become the owner. | Needs a test privacy request. Use test data only.
PMCM Admin | AD-PRV | AD-PRV · Privacy Console | AD-PRV-02 | Approve, reject and execute | Approve and execute an access/export request on test data. Reject another. | Execution returns the subject's data bundle. Rejection is recorded. | Needs a test privacy request. Use test data only.
PMCM Admin | AD-PRV | AD-PRV · Privacy Console | AD-PRV-03 | Legal hold | Place a legal hold, then lift it. | While on hold, related deletion is blocked. Lifting the hold is recorded. | Needs a test privacy request. Use test data only.
PMCM Admin | AD-SET | AD-SET · Settings | AD-SET-01 | Client event-day view switch | Open Settings and turn the Client event-day view switch on and off. | A saving state appears and the setting stays after reload. | Sign in as admin.
Coordinator | CO-ACC | CO-ACC · Sign-in and Portal Scope | CO-ACC-01 | Sign in | Sign in with the coordinator email and password. | The Coordinator Portal opens, not the PMCM command portal. | Use the coordinator account issued for UAT.
Coordinator | CO-ACC | CO-ACC · Sign-in and Portal Scope | CO-ACC-02 | PMCM areas are closed | Type PMCM addresses such as /dashboard/finance or /dashboard/audit. | Only the Coordinator Portal is shown. No finance, audit, inquiry or supplier data is visible. | Use the coordinator account issued for UAT.
Coordinator | CO-ACC | CO-ACC · Sign-in and Portal Scope | CO-ACC-03 | Role notice | Read the boundary notice. | It says coordinators only see data for their role. | Use the coordinator account issued for UAT.
Coordinator | CO-EVT | CO-EVT · Event Switcher and Assignment | CO-EVT-01 | Assigned events only | Open the event switcher. | Only events you are assigned to are listed, including past ones. | Needs at least one assignment from PMCM.
Coordinator | CO-EVT | CO-EVT · Event Switcher and Assignment | CO-EVT-02 | Acknowledge or decline | Acknowledge a new assignment. On another test assignment, decline or withdraw. | Each action is recorded and appears in assignment history. | Needs at least one assignment from PMCM.
Coordinator | CO-EVT | CO-EVT · Event Switcher and Assignment | CO-EVT-03 | Archived events | Switch to an archived event. | A read-only banner is shown and all forms are disabled. | Needs at least one assignment from PMCM.
Coordinator | CO-DAY | CO-DAY · Event Day Work | CO-DAY-01 | Mark arrival | Mark your arrival. | Your attendance shows as arrived. | Select a current event you are assigned to.
Coordinator | CO-DAY | CO-DAY · Event Day Work | CO-DAY-02 | Role queue | Update the status of a task in your queue. | The new status is saved. | Select a current event you are assigned to.
Coordinator | CO-DAY | CO-DAY · Event Day Work | CO-DAY-03 | Request reassignment | Request reassignment of a task with a reason and a new role or coordinator. | The request is sent to the operator or PMCM. | Select a current event you are assigned to.
Coordinator | CO-DAY | CO-DAY · Event Day Work | CO-DAY-04 | Log task and urgent issue | Log an event-day task with priority and due time, and an urgent issue with severity and area. | Both are recorded and PMCM can see them in Live ops. | Select a current event you are assigned to.
Coordinator | CO-DAY | CO-DAY · Event Day Work | CO-DAY-05 | Timeline and briefing | Open the timeline and briefing. | The critical timeline and floor and stage briefing are shown, or a message if PMCM has not submitted the briefing. | Select a current event you are assigned to.
Coordinator | CO-OPR | CO-OPR · Event Day System Operator | CO-OPR-01 | Delegated attendance | Mark another coordinator absent with Confirm absent. | Their attendance is updated. | Sign in as the coordinator PMCM designated as operator. Some cases need a second, non-operator coordinator.
Coordinator | CO-OPR | CO-OPR · Event Day System Operator | CO-OPR-02 | Reassignment decisions | Approve one reassignment request and reject another. | Both decisions are recorded and the task owner updates. | Sign in as the coordinator PMCM designated as operator. Some cases need a second, non-operator coordinator.
Coordinator | CO-OPR | CO-OPR · Event Day System Operator | CO-OPR-03 | Edit the schedule | Add a day and a segment. | The schedule is updated. | Sign in as the coordinator PMCM designated as operator. Some cases need a second, non-operator coordinator.
Coordinator | CO-OPR | CO-OPR · Event Day System Operator | CO-OPR-04 | Non-operator cannot edit | Sign in as a non-operator coordinator and open the schedule. | A message says only the designated operator can edit the schedule. | Sign in as the coordinator PMCM designated as operator. Some cases need a second, non-operator coordinator.
Coordinator | CO-SUP | CO-SUP · Supplier Setup Checks | CO-SUP-01 | Verify setup | Verify a supplier's setup. | The setup shows as verified and PMCM sees it. | Sign in as the operator or an Ingress and Egress coordinator.
Coordinator | CO-SUP | CO-SUP · Supplier Setup Checks | CO-SUP-02 | Dispute setup | Dispute another supplier's setup with a note. | The dispute is recorded and PMCM sees it. | Sign in as the operator or an Ingress and Egress coordinator.
Coordinator | CO-REG | CO-REG · Registration Desk | CO-REG-01 | Search the roster | Search the guest roster by name. | Matching guests are listed with limited details. | Sign in as a Registration Staff coordinator assigned to the event.
Coordinator | CO-REG | CO-REG · Registration Desk | CO-REG-02 | Check in a guest | Verify and check in a guest. | The guest shows as checked in. | Sign in as a Registration Staff coordinator assigned to the event.
Coordinator | CO-REG | CO-REG · Registration Desk | CO-REG-03 | Register a walk-in | Register a walk-in without consent, then with consent, then verify and check them in. | Consent is required. The walk-in follows the PMCM walk-in policy and can be checked in after verification. | Sign in as a Registration Staff coordinator assigned to the event.
Coordinator | CO-REG | CO-REG · Registration Desk | CO-REG-04 | Archived event | Switch to an archived event and try to check in a guest. | The roster can be read but check-in is refused. | Sign in as a Registration Staff coordinator assigned to the event.

## Responses
Submission ID | Test Date | Tester | User Role | Module | Test Case ID | Test Case | Satisfaction Level | Comment | Check

## Summary
UAT Summary
Counts come from the Responses sheet. Pass rate = Passed ÷ results recorded.
Role | Module | Test Cases | Passed | Partially Passed | Fail | Skipped | Results Recorded | Pass Rate | Comments Missing
Client | All Client modules
Client | CL-INQ · Public Inquiry
Client | CL-ACC · Sign-in and Account Access
Client | CL-CON · Conforme
Client | CL-DSH · Dashboard and My Events
Client | CL-REQ · New Event Request
Client | CL-EVT · Event Workspace and Change Requests
Client | CL-BRF · Briefing and Proposal
Client | CL-FLR · Floor Plan
Client | CL-FIL · Files and Documents
Client | CL-BIL · Billing
Client | CL-MSG · Messages
Client | CL-CAL · Calendar and Approvals
Client | CL-CLO · Event Closeout
Supplier | All Supplier modules
Supplier | SU-APP · Supplier Application
Supplier | SU-ACC · Sign-in and Account Access
Supplier | SU-DSH · Dashboard Overview and Calendar
Supplier | SU-QUO · Quote Requests and Quotations
Supplier | SU-BKG · Bookings, Contracts and Event Day
Supplier | SU-FIL · Files, Payments and Profile
Supplier | SU-MSG · Messages
Guest | All Guest modules
Guest | GU-OPN · Open Event with Access Code
Guest | GU-PAS · Event Pass and Details
Guest | GU-CHK · Check-in
Guest | GU-FBK · Feedback
Guest | GU-GAM · Event Games
PMCM Admin | All PMCM Admin modules
PMCM Admin | AD-ACC · Sign-in and Account Access
PMCM Admin | AD-INB · Dashboard and Command Inbox
PMCM Admin | AD-INQ · Inquiries and Client Onboarding
PMCM Admin | AD-CLI · Clients
PMCM Admin | AD-TSK · Tasks and Ocular Visits
PMCM Admin | AD-OVR · Event Overview, Briefing and Change Control
PMCM Admin | AD-FLR · Floorplans
PMCM Admin | AD-SUP · Event Suppliers
PMCM Admin | AD-DIR · Supplier Directory and Applications
PMCM Admin | AD-COR · Coordinators and Team
PMCM Admin | AD-LIV · Live Ops and Run Sheet
PMCM Admin | AD-REG · Registration and Guests
PMCM Admin | AD-GAM · Event Games
PMCM Admin | AD-BIL · Billing and Finance
PMCM Admin | AD-CLO · Closure and Archive
PMCM Admin | AD-MSG · Messages
PMCM Admin | AD-FIL · Files and Requirements
PMCM Admin | AD-AUD · Audit Trail and Decision Log
PMCM Admin | AD-PRV · Privacy Console
PMCM Admin | AD-SET · Settings
Coordinator | All Coordinator modules
Coordinator | CO-ACC · Sign-in and Portal Scope
Coordinator | CO-EVT · Event Switcher and Assignment
Coordinator | CO-DAY · Event Day Work
Coordinator | CO-OPR · Event Day System Operator
Coordinator | CO-SUP · Supplier Setup Checks
Coordinator | CO-REG · Registration Desk
Total

## Lists (hidden)
Roles | Satisfaction Level | Role | Module
Client | Passed - Working | Client | CL-INQ · Public Inquiry
Supplier | Partially Passed - Works but needs revision (w/ comment) | Client | CL-ACC · Sign-in and Account Access
Guest | Fail - Not working | Client | CL-CON · Conforme
PMCM Admin | Skipped - Di tinest (w/ comment) | Client | CL-DSH · Dashboard and My Events
Coordinator |  | Client | CL-REQ · New Event Request
|  | Client | CL-EVT · Event Workspace and Change Requests
|  | Client | CL-BRF · Briefing and Proposal
|  | Client | CL-FLR · Floor Plan
|  | Client | CL-FIL · Files and Documents
|  | Client | CL-BIL · Billing
|  | Client | CL-MSG · Messages
|  | Client | CL-CAL · Calendar and Approvals
|  | Client | CL-CLO · Event Closeout
|  | Supplier | SU-APP · Supplier Application
|  | Supplier | SU-ACC · Sign-in and Account Access
|  | Supplier | SU-DSH · Dashboard Overview and Calendar
|  | Supplier | SU-QUO · Quote Requests and Quotations
|  | Supplier | SU-BKG · Bookings, Contracts and Event Day
|  | Supplier | SU-FIL · Files, Payments and Profile
|  | Supplier | SU-MSG · Messages
|  | Guest | GU-OPN · Open Event with Access Code
|  | Guest | GU-PAS · Event Pass and Details
|  | Guest | GU-CHK · Check-in
|  | Guest | GU-FBK · Feedback
|  | Guest | GU-GAM · Event Games
|  | PMCM Admin | AD-ACC · Sign-in and Account Access
|  | PMCM Admin | AD-INB · Dashboard and Command Inbox
|  | PMCM Admin | AD-INQ · Inquiries and Client Onboarding
|  | PMCM Admin | AD-CLI · Clients
|  | PMCM Admin | AD-TSK · Tasks and Ocular Visits
|  | PMCM Admin | AD-OVR · Event Overview, Briefing and Change Control
|  | PMCM Admin | AD-FLR · Floorplans
|  | PMCM Admin | AD-SUP · Event Suppliers
|  | PMCM Admin | AD-DIR · Supplier Directory and Applications
|  | PMCM Admin | AD-COR · Coordinators and Team
|  | PMCM Admin | AD-LIV · Live Ops and Run Sheet
|  | PMCM Admin | AD-REG · Registration and Guests
|  | PMCM Admin | AD-GAM · Event Games
|  | PMCM Admin | AD-BIL · Billing and Finance
|  | PMCM Admin | AD-CLO · Closure and Archive
|  | PMCM Admin | AD-MSG · Messages
|  | PMCM Admin | AD-FIL · Files and Requirements
|  | PMCM Admin | AD-AUD · Audit Trail and Decision Log
|  | PMCM Admin | AD-PRV · Privacy Console
|  | PMCM Admin | AD-SET · Settings
|  | Coordinator | CO-ACC · Sign-in and Portal Scope
|  | Coordinator | CO-EVT · Event Switcher and Assignment
|  | Coordinator | CO-DAY · Event Day Work
|  | Coordinator | CO-OPR · Event Day System Operator
|  | Coordinator | CO-SUP · Supplier Setup Checks
|  | Coordinator | CO-REG · Registration Desk